## Sheet1
| List of Reqirements (planned to implement) | Specification (what I implemented) | Progress | Time spend
User Accounts
1 | User can create account | Create user account with name, email, password, zip code and title include Doctor, nurse, Medical supplier and Pharmaceutical supplier | done | 3
2 | User can Login the account | User can login the account, it shows up error if the user name or password is wrong | done | 3
3 | Security | The password was hashed | done | 1
4 | Profile function | user can update the profile in dashboard, for instance, update the name, zip code and so on | done | 2
Search Functionality
1 | Basic search function | user can search by name | done | 3
2 | Advanced search options based on zip code, title | user can search by zip code and title | done | 3
Messaging System
1 | Functionality to send messages after search | after search, user can send message directly to the person | done | 4
2 | User can send and receive message in the message page | in the message box, I can see the message, reply message | done | 3
Booking/Appointment System
1 | Functionality to send requests after search | user can send request once the there is availible time slot | done | 3
2 | User can create, add ,delete, approve the request | in the calendar page, user can create add, delete, approve, disapprove the request | done | 12 | I tried to use google canlendar API, I have connected to the API however the next steps are two complex for me. And then I create new table for this, I spend more than 10 hours on this
UI/UX Design
1 | Easy to use, clean, and intuitive design. | The theme is very suited for Medical Scheduling Platform | done | 3
|  |  | Total | 40